## Sheet1
Risks | Response Strategy | Objectives | Baseline
Operational Risks |  |  | Likelihood | Impact | Risk Level
The unique nature of the application may present estimation and scheduling issues | Ensure that the client is presented with a timescale that is longer than the time expected to MVP | To have a MVP in three weeks | Unlikely | Very High | 55%
Failure to address priority conflicts may lead to important features being left out | Use MOSCOW to priotise each feature | To ensure the MVP includes all the must-have features | Very Unlikely | Very High | 40%
Insufficient resources to meet MVP | Ensure that all software and packages are correctly installed before beginning the project | To make sure that the MVP can be deployed using available resources | Very Unlikely | High | 35%
Security Risks |  |  | Likelihood | Impact | Risk Level
SQL Injection | Use parameterised queries instead of string concatenation or stored procedures | Ensure that the application is protected against SQL injections | Unlikely | Very High | 50%
DDoS Attack | Attack detection, upstream filtering and allowing/denying specific IP addresses | Ensure that the application is protected against DDoS attacks | Unlikely | Very High | 50%
Objectives Risks |  |  | Likelihood | Impact | Risk Level
Application does not meet the required expectation on testing | Ensure regular testing and coverage testing | Ensure that the application passes at least 90% | Likely | High | 75%